## Instructions
Seatwise — Acceptance Test Plan
Companion to the Seatwise Product Requirements Document. Version 1.0 · Prepared for Tom Carter, E-gineering
Purpose
Every row on the "Test Cases" tab is a single, self-contained acceptance test derived directly from one requirement in the Seatwise PRD. Each one can be executed and judged pass/fail by someone who has never seen the app or its design before — no knowledge of how it was built is required, only the ability to follow the numbered steps and compare the result to what's expected.
How to use this workbook
1. Open the "Test Cases" tab. Use the filter arrows on the header row to narrow to a Feature Area, Type, or Priority you want to run — for example, filter Priority = Must to run the safety-critical tests first, or Feature Area = Day-Of / Emergency Mode to test one area in isolation.
2. For each row, set up whatever the Preconditions column describes, then follow the numbered Test Steps exactly.
3. Compare what actually happens to the Expected Result column.
4. Set the Status cell using the dropdown: Pass, Fail, Blocked, or N/A (see definitions below). Rows start as "Not Run."
5. Fill in Tested By and Date Tested.
6. If the result was Fail or Blocked, describe exactly what happened in Notes — what you saw instead of the expected result — so it can be reproduced.
Status definitions
Pass — what you observed matches the Expected Result exactly.
Fail — what you observed does not match the Expected Result. Explain the actual behavior in Notes.
Blocked — the test could not be run at all, usually because an earlier, unrelated test failed first. Explain what blocked it in Notes.
N/A — the requirement does not apply in this build or environment (e.g., a feature intentionally not yet built). Explain why in Notes.
Column reference
Requirement Ref — the requirement ID(s) from the PRD this test verifies (e.g., FR-3.2). Open the PRD and search for that ID for full context if a step is ever unclear.
Type — Positive (confirms the feature works as intended), Negative (confirms the system correctly blocks or rejects something it should), Boundary/Performance/Security/Accessibility (specialized checks), or End-to-End (a full multi-step scenario spanning several requirements).
Priority — Must (safety-critical or core to the product; a failure here should block release) or Should (important but not release-blocking on its own).
Example of a completed row
ID: EX-1
Requirement Ref: FR-1.1
Feature Area: Account & Wedding Management
Scenario: Create an account with multiple weddings
Type: Positive
Priority: Must
Preconditions: No existing planner account.
Test Steps: 1. Create a new planner account. 2. Create a wedding named "Test Wedding A." 3. Create a second wedding named "Test Wedding B."
Expected Result: Both weddings exist under the same account and can each be opened independently.
Status: Pass
Tested By: J. Rivera
Date Tested: 2026-09-10
Notes: Both weddings created and opened without issue.
Tip: this example row is for reference only — it is not part of the Test Cases tab and should not be edited.

## Test Cases
ID | Requirement Ref | Feature Area | Scenario | Type | Priority | Preconditions | Test Steps | Expected Result | Status | Tested By | Date Tested | Notes
AC-001 | FR-0.1 | Cross-Cutting Invariant | Hard rules cannot be violated by any direct action | Negative | Must | A wedding has: a Must-Not-Sit-Together rule, one table already at full capacity, and one Restricted table with an explicit guest list. | 1. Attempt to manually seat two Must-Not-Sit-Together guests at the same table. 2. Attempt to seat any guest at the table that is already full. 3. Attempt to seat a guest who is NOT on a Restricted table's list at that table. | All three attempts are blocked before taking effect. Each shows a plain-language message naming the specific rule and guests involved. No option to override is offered. | Not Run
AC-002 | FR-0.1 | Cross-Cutting Invariant | Indirect hard-rule violation flags the guest instead of hiding it | Negative | Must | Guest is already seated at Table 5. A Must-Not-Sit-Together rule does not yet apply to their tablemate. | 1. Edit the guest's household so a Must-Not-Sit-Together rule now applies between them and their current tablemate at Table 5. | The guest is visibly flagged as needing reassignment. The plan is not saved or displayed as if everything were fine. No other guest is moved automatically. | Not Run
AC-003 | FR-0.2 | Cross-Cutting Invariant | Soft-rule violations warn but never block | Positive | Must | A Prefer-Near rule exists between two guests currently seated at different tables. | 1. Open the seating plan and locate the two guests. | Their being apart is shown as a visible, non-blocking warning somewhere in the plan view. Nothing about the plan is blocked or prevented because of it. | Not Run
AC-004 | FR-1.1 | Account & Wedding Management | Create an account with multiple weddings | Positive | Must | No existing planner account. | 1. Create a new planner account. 2. Create a wedding named "Test Wedding A." 3. Create a second wedding named "Test Wedding B." | Both weddings exist under the same account and can each be opened independently. | Not Run
AC-005 | FR-1.2 | Account & Wedding Management | Wedding data is fully isolated from other weddings on the same account | Negative | Must | One planner account owns Wedding A and Wedding B, each with at least one guest. | 1. Add a unique guest to Wedding A. 2. Open Wedding B and look through its guest list, rules, tables, and plan. | The guest added to Wedding A does not appear anywhere in Wedding B. | Not Run
AC-006 | FR-1.3 | Account & Wedding Management | Enter and save basic wedding details | Positive | Should | A new wedding is being created. | 1. Enter couple's names, wedding date, and venue name. 2. Leave the optional note field blank and save. 3. Reopen the wedding. | All entered fields are saved and redisplay correctly; the blank note field is accepted without error. | Not Run
AC-007 | FR-1.3a | Account & Wedding Management | Custom side labels apply everywhere Side is shown | Positive | Should | A wedding exists with at least 3 guests using the default side labels. | 1. In wedding settings, rename the two side labels (e.g., to "Partner A" / "Partner B"). 2. Open the guest list and the rules screen. | Every place Side is shown now uses the new labels. No guest's side data is lost or reset. | Not Run
AC-008 | FR-1.4 | Account & Wedding Management | Invite a collaborator with a specific permission level | Positive | Must | A wedding exists. | 1. Invite an email address to the wedding with Comment-only permission. | An invitation is sent. The person shows as "Invited" with Comment permission until they accept. | Not Run
AC-009 | FR-1.4a | Account & Wedding Management | Invited person must authenticate before seeing any data | Negative | Must | An invitation email has been sent to a new user who has never logged in. | 1. Open the invitation link without signing in. 2. Inspect the invitation email itself. | No wedding data is shown until the person signs in or creates an account. The email itself contains no guest data. | Not Run
AC-010 | FR-1.5 | Account & Wedding Management | Invited collaborator sees only the wedding(s) they were invited to | Negative | Must | Planner owns Wedding A and Wedding B. A collaborator is invited only to Wedding A. | 1. Log in as that collaborator. 2. Look for any way to view or discover Wedding B. | Only Wedding A is visible. There is no list, link, or trace of Wedding B anywhere in the collaborator's view. | Not Run
AC-011 | FR-1.6 | Account & Wedding Management | Revoking access takes effect immediately | Negative | Must | A collaborator currently has access to a wedding. | 1. As the planner, revoke that collaborator's access. 2. As the collaborator, try to open the wedding again (including via a previously saved link). | Access is denied immediately; the wedding is no longer visible or reachable by that person. | Not Run
AC-012 | FR-2.1 | Guest List Management | Create a guest with only a name; defaults apply | Positive | Must | A wedding exists. | 1. Add a new guest with only a full name entered; leave Side and Relationship Tier blank. 2. Save and reopen the guest record. | Guest saves successfully. Side defaults to "Both" and Relationship Tier defaults to "Guest." Both fields can be edited afterward. | Not Run
AC-013 | FR-2.2 | Guest List Management | Optional guest fields save correctly | Positive | Should | A wedding exists. | 1. Add a guest with a plus-one indicator, a dietary note, an accessibility note, age category "Child," and a free-text note. | All fields save and display correctly on the guest record. | Not Run
AC-014 | FR-2.2a | Guest List Management | Plus-one is created as its own record, even before their name is known | Positive | Should | An existing guest is being marked as bringing a plus-one. | 1. Mark the guest as bringing a plus-one before knowing their name; confirm a placeholder guest (e.g., "[Guest]'s Guest") is created in the same household. 2. Create a seating rule involving that placeholder. 3. Rename the placeholder to the real guest's name. | The placeholder is a full, independent guest record from step 1. Renaming it in step 3 does not remove or break the rule created in step 2, or change any existing seat assignment. | Not Run
AC-015 | FR-2.3 | Guest List Management | Add, edit, and remove a single guest | Positive | Must | A wedding exists. | 1. Add a guest through the form. 2. Edit that guest's name. 3. Remove the guest. | Each action succeeds and the guest list reflects it immediately. | Not Run
AC-016 | FR-2.4 | Guest List Management | Bulk import reports per-row errors specifically | Negative | Must | A spreadsheet with 10 valid guest rows and 2 invalid rows (e.g., one missing a name) is ready to import. | 1. Import the spreadsheet, mapping columns to Seatwise fields. | The 10 valid rows import successfully. The 2 invalid rows are each reported with a specific reason tied to that row (e.g., "row 4: missing name") — not one generic failure message. | Not Run
AC-017 | FR-2.4a | Guest List Management | Import preview shows new-vs-updated counts before anything is written | Positive | Must | An import spreadsheet has some rows matching existing guests by a mapped ID column, and some new rows. | 1. Start an import and map the matching-key column. 2. View the preview screen without confirming. 3. Cancel instead of confirming. | The preview clearly shows counts of rows that will be added as new vs. rows that will update existing guests. Canceling in step 3 leaves the guest list completely unchanged. | Not Run
AC-018 | FR-2.5 | Guest List Management | Household is a soft default; an explicit rule makes it hard | Positive | Must | Three guests are grouped into one household with no other rule. | 1. Manually move one household member to a different table; confirm it succeeds. 2. Add an explicit Must-Sit-Together rule for the same household. 3. Attempt the same move again. | Step 1 succeeds (household grouping alone is only a soft preference). Step 3 is blocked, since the explicit rule makes it a hard rule. | Not Run
AC-019 | FR-2.6 | Guest List Management | Search, filter, and sort the guest list | Positive | Should | A guest list with guests on both sides, multiple tiers, and some unassigned. | 1. Search by a guest's name. 2. Filter by side. 3. Filter by "unassigned." 4. Sort by relationship tier. | Each operation returns the correct, expected result set or order. | Not Run
AC-020 | FR-2.7 | Guest List Management | Unseated guests are surfaced prominently | Positive | Should | A guest exists who has not been assigned to a table. | 1. View the guest list. | The unseated guest is clearly marked, and unseated guests overall are easy to find (e.g., a dedicated filter, count, or highlighted section). | Not Run
AC-021 | FR-2.8 | Guest List Management | Guests with the same name are visually disambiguated everywhere | Positive | Should | Two different guests are both named "John Smith," from different households. | 1. Search the guest list for "John Smith." 2. Open a rule-creation screen and search for "John Smith" there. | Both guests appear as distinct entries in both places, each showing distinguishing information (e.g., household or side) alongside the name. | Not Run
AC-022 | FR-2.9 | Guest List Management | Editing a guest re-checks their existing seat against hard rules | Negative | Must | A guest is seated at a table with someone who is not currently subject to any rule. | 1. Edit the guest's household to one that has a Must-Not-Sit-Together rule against their current tablemate. | The guest is flagged as needing reassignment. No hard-rule violation is left silently in place. | Not Run
AC-023 | FR-3.1 | Relationships & Seating Rules | Must-Sit-Together is enforced by both generation and manual editing | Positive | Must | Two guests exist with no table assignment yet. | 1. Create a Must-Sit-Together rule linking them. 2. Run auto-generation. 3. Attempt to manually move one of them away from the other. | Generation always seats both at the same table. The manual move in step 3 is blocked. | Not Run
AC-024 | FR-3.2 | Relationships & Seating Rules | Must-Not-Sit-Together is enforced by both generation and manual editing | Negative | Must | Two guests exist with no table assignment yet. | 1. Create a Must-Not-Sit-Together rule linking them. 2. Run auto-generation. 3. Attempt to manually seat them at the same table. | Generation never seats them together. The manual move in step 3 is blocked. | Not Run
AC-025 | FR-3.3 | Relationships & Seating Rules | Prefer-Near / Prefer-Avoid influence generation but never block a manual move | Positive | Should | Two guest pairs exist, unassigned. | 1. Create a Prefer-Near rule for pair 1 and a Prefer-Avoid rule for pair 2. 2. Run auto-generation. 3. Manually move a guest in a way that works against one of these rules. | Generation favors satisfying both rules where possible. The manual move in step 3 is allowed, with a visible warning rather than being blocked. | Not Run
AC-026 | FR-3.4 | Relationships & Seating Rules | Side-Mixing levels change generation behavior; a table can override | Positive | Must | A guest list with a roughly even split across both sides. | 1. Set Side-Mixing to "Keep sides separate" and generate; note the table composition. 2. Change to "Fully mixed" and regenerate; note the composition. 3. Mark one specific table "single-side only" and regenerate again. | Step 1 shows tables noticeably grouped by side. Step 2 shows tables noticeably blended. Step 3's marked table stays single-side regardless of the wedding-level setting. | Not Run
AC-027 | FR-3.5 | Relationships & Seating Rules | Creating a hard rule that contradicts an existing hard rule is blocked | Negative | Must | A Must-Sit-Together rule already exists between Guest A and Guest B. | 1. Attempt to create a Must-Not-Sit-Together rule between the same Guest A and Guest B. | Creation is blocked. A plain-language message names the earlier, conflicting Must-Sit-Together rule. The contradictory rule is not saved. | Not Run
AC-028 | FR-3.5a | Relationships & Seating Rules | A soft-rule contradiction is allowed but flagged | Positive | Should | Guests C and D exist with no rules between them. | 1. Create a Prefer-Near rule between C and D. 2. Create a Prefer-Avoid rule between the same C and D. | Both rules save successfully. A visible warning appears on both rules, including wherever rules are listed. | Not Run
AC-029 | FR-3.6 | Relationships & Seating Rules | All rules are visible and manageable from one dedicated list | Positive | Should | Several rules of different types exist across different guests. | 1. Open the dedicated rules list. | Every rule created anywhere in the wedding appears in this one list and can be edited or removed from it directly. | Not Run
AC-030 | FR-3.7 | Relationships & Seating Rules | A Purpose table is a soft suggestion, not a hard cap | Positive | Should | More child guests exist than a "Kids' Table" has capacity for. | 1. Label a table "Kids' Table" (Purpose, not Restricted). 2. Run auto-generation. | The table favors seating children there, but overflow children are seated elsewhere rather than the generation failing or the table exceeding capacity. | Not Run
AC-031 | FR-3.7a | Relationships & Seating Rules | A Restricted table only ever holds its explicitly listed guests | Negative | Must | A table is marked Restricted with an explicit list of exactly 2 guests. | 1. Run auto-generation. 2. Attempt to manually add a third guest, who is not on the list, to that table. | Generation seats only the 2 listed guests at that table (never anyone else). The manual add in step 2 is blocked. | Not Run
AC-032 | FR-3.8 | Relationships & Seating Rules | Accessible-seating requirement is enforced as a hard rule | Negative | Must | One guest is flagged as requiring accessible seating. Only one table is marked Accessible. | 1. Run auto-generation. 2. Attempt to manually move that guest to a table not marked Accessible. | Generation always seats the guest at the Accessible table. The manual move in step 2 is blocked. | Not Run
AC-033 | FR-4.1 | Table & Venue Layout | Tables can be defined with each shape option and a capacity | Positive | Should | A wedding exists with no tables yet. | 1. Create one table of each shape option, including "Other" with a custom free-text label. 2. Set a seat capacity on each. | All tables save with their shape and capacity. Shape only changes how the table is drawn on the floor plan; it has no effect on seating behavior. | Not Run
AC-034 | FR-4.2 | Table & Venue Layout | A standard set of tables can be created in one action | Positive | Should | A wedding exists with no tables yet. | 1. Use the quick-create option to generate "12 round tables of 8." | 12 tables are created in a single action, each with capacity 8, with no need to add them one at a time. | Not Run
AC-035 | FR-4.3 | Table & Venue Layout | The floor plan is fully optional | Positive | Should | A wedding is fully set up (guests, rules, tables). | 1. Complete a full generate-review-approve cycle without ever opening the floor plan view. 2. Separately, open the floor plan and drag a table to a new position. | The entire workflow in step 1 works with no floor-plan use at all. The floor plan in step 2 successfully repositions the table. | Not Run
AC-036 | FR-4.4 | Table & Venue Layout | Table capacity is enforced in both manual editing and generation | Negative | Must | One table is filled to its exact stated capacity. Total guests across the wedding exceed total seats. | 1. Attempt to manually add one more guest to the full table. 2. Run auto-generation with more guests than total seats available. | Step 1 is blocked. Step 2 does not overfill any table — it is reported as impossible per FR-5.2, not silently forced. | Not Run
AC-037 | FR-4.5 | Table & Venue Layout | Seats-vs-guests shortfall is shown clearly | Positive | Should | Total guests exceed total available seats. | 1. View the wedding overview/summary. 2. Add enough seats (or remove guests) so seats are now sufficient, and view the overview again. | Step 1 shows a clear warning about the shortfall. Step 2 shows no warning once seats are sufficient. | Not Run
AC-038 | FR-4.6 | Table & Venue Layout | A table can be marked Accessible and the flag is visible | Positive | Should | A table exists. | 1. Mark the table Accessible. 2. View the table's details, then toggle the flag off. | The Accessible flag saves, displays clearly on the table, and can be toggled off again. | Not Run
AC-039 | FR-4.7 | Table & Venue Layout | No feature exists for assigning a specific chair/seat number | Positive | Should | Any wedding with tables and seated guests. | 1. Look for any control, anywhere in the product, for assigning a guest to a specific numbered seat within a table. | No such control exists. Assignment is always guest-to-table only. | Not Run
AC-040 | FR-5.1 | Automated Seat Assignment Engine | One action produces a complete first-draft plan | Positive | Must | A wedding has a complete guest list, tables, and rules with no contradictions. | 1. Click Generate. | Every guest is assigned to exactly one table in a single action. | Not Run
AC-041 | FR-5.2 / 10.2 | Automated Seat Assignment Engine | An impossible hard-rule set is reported, never silently forced | Negative | Must | A Must-Sit-Together group is larger than the capacity of any single table in the wedding. | 1. Run auto-generation. | No plan is produced. A report names exactly which guests/rules could not be placed and why. No partial or rule-violating plan is saved or displayed. | Not Run
AC-042 | FR-5.3 | Automated Seat Assignment Engine | Generation reports how well soft preferences were satisfied | Positive | Should | A normal, fully satisfiable wedding setup with some Prefer-Near rules. | 1. Run auto-generation. | A summary is shown of how well soft preferences were satisfied (e.g., a percentage of Prefer-Near requests honored). | Not Run
AC-043 | FR-5.4 | Automated Seat Assignment Engine | Generation can be re-run repeatedly | Positive | Should | A plan has already been generated once. | 1. Change a rule. 2. Regenerate. 3. Regenerate again with no changes. | Each regeneration produces a new, retrievable draft reflecting the current inputs at that time. | Not Run
AC-044 | FR-5.5 / 10.3 | Automated Seat Assignment Engine | Locking preserves placements and avoids needless reshuffling | Positive | Must | An existing generated plan with several tables filled. | 1. Lock 2 tables. 2. Add one new guest. 3. Regenerate. | Guests at the 2 locked tables are completely unchanged. Guests at unlocked tables who were unaffected by the new guest also remain largely unchanged. The new guest is placed appropriately. | Not Run
AC-045 | FR-5.6 | Automated Seat Assignment Engine | Each generation run is saved as a distinct, retrievable version | Positive | Should | A wedding ready for generation. | 1. Generate. 2. Make a small change. 3. Generate again. 4. Open version history. | Two distinct versions exist in history, each individually retrievable. | Not Run
AC-046 | FR-5.1 / 9.1 | Automated Seat Assignment Engine | Generation completes within the performance target at typical scale | Performance | Must | A wedding with 300 guests and 40 tables, satisfiable rule set. | 1. Run auto-generation and time it from click to completed plan. | Generation completes in under 15 seconds. | Not Run
AC-047 | FR-6.1 | Review & Approval | Both a visual layout and a list view are available and consistent | Positive | Should | A generated plan exists. | 1. Open the visual, table-by-table layout view. 2. Switch to the guest-to-table list view. | Both views are available and show the same, consistent assignment data. | Not Run
AC-048 | FR-6.2 | Review & Approval | Sharing respects each person's permission level | Positive | Must | A plan exists. One collaborator has View-only permission, another has Edit permission. | 1. Share the plan; have the View-only collaborator open it and attempt to move a guest. 2. Have the Edit collaborator open it and move a guest. | The View-only collaborator cannot make the move in step 1. The Edit collaborator's move in step 2 succeeds. | Not Run
AC-049 | FR-6.3 | Review & Approval | Comments can be left on a table or on a specific guest's placement | Positive | Should | A plan is shared with a collaborator who has Comment permission. | 1. Leave a comment on a specific table. 2. Leave a comment on a specific guest's placement. | Both comments save, are attributed to the commenter, and are visible to everyone with access. | Not Run
AC-050 | FR-6.4 | Review & Approval | Only the Planner/Owner or Couple can mark a plan Approved | Negative | Must | A plan is in Draft status. A Collaborator (not Planner, not Couple) has Edit permission. | 1. As the Collaborator, move the plan from Draft to In Review. 2. As the same Collaborator, attempt to mark the plan Approved. 3. As the Planner, mark the plan Approved. | Step 1 succeeds. Step 2 is not permitted — no Approve action is available or it is blocked. Step 3 succeeds. | Not Run
AC-051 | FR-6.5 | Review & Approval | Approving a plan does not prevent further edits | Positive | Must | A plan is Approved. | 1. Make a manual edit to the approved plan. | The edit is allowed and takes effect; approval did not lock or freeze the plan. | Not Run
AC-052 | FR-6.6 | Review & Approval | Editing an approved plan shows a Modified-since-approval indicator | Positive | Should | A plan is Approved. | 1. Make an edit. 2. View the plan's status area. | Status still reads Approved. A "Modified since approval" indicator appears with a timestamp and the editor's name. No re-approval step was required for the edit to take effect. | Not Run
AC-053 | FR-7.1 | Manual Adjustment | A guest can be dragged from one table to another | Positive | Must | A plan exists with a guest at Table 1 and no rule conflicts with Table 2. | 1. Drag the guest from Table 1 to Table 2 in the visual view. | The guest moves successfully and the change is reflected immediately in both the visual and list views. | Not Run
AC-054 | FR-7.2 | Manual Adjustment | Every kind of hard-rule-breaking move is blocked outright, with no override | Negative | Must | A wedding has: a full table, a Must-Sit-Together group, a Must-Not-Sit-Together pair, a Restricted table, and an accessible-seating guest. | Attempt, one at a time: (1) exceed a table's capacity; (2) split a Must-Sit-Together group; (3) combine a Must-Not-Sit-Together pair; (4) add a non-listed guest to a Restricted table; (5) move an accessible-seating guest off the Accessible table. | All five attempts are blocked, each with a plain-language explanation naming the specific rule and guests. None offers an override option. | Not Run
AC-055 | FR-7.3 | Manual Adjustment | A soft-rule-breaking move is allowed with a warning | Positive | Should | A Prefer-Near rule links two guests seated together. | 1. Manually move one of them away from the other. | The move succeeds. A visible, non-blocking warning is shown. | Not Run
AC-056 | FR-7.4 | Manual Adjustment | Locking protects a guest from auto-generation but not from manual edits | Positive | Should | A generated plan exists. | 1. Lock one guest. 2. Regenerate the plan. 3. Manually move the locked guest. | The locked guest is unchanged after step 2's regeneration. The manual move in step 3 still succeeds. | Not Run
AC-057 | FR-7.5 | Manual Adjustment | Manual edits support undo and redo | Positive | Should | A plan exists. | 1. Manually move a guest. 2. Undo. 3. Redo. | Undo reverts the move exactly; redo reapplies it exactly. | Not Run
AC-058 | FR-7.6 | Manual Adjustment | Every manual edit is recorded with who and when | Positive | Should | A plan exists. | 1. Make a manual edit. 2. Open the plan's change history. | The edit appears in the history with the correct user and timestamp. | Not Run
AC-059 | FR-7.7 | Manual Adjustment | Concurrent edits by two users don't silently overwrite each other | Negative | Must | Two users with Edit permission have the same plan open at the same time. | 1. User A moves Guest X to Table 3. 2. Confirm User B's screen reflects that move within 5 seconds without a manual refresh. 3. Without refreshing, have User B attempt to move Guest X (already moved by A) somewhere else, based on B's stale view. | Step 2's update appears within 5 seconds. Step 3 does not silently overwrite A's change — B is shown the current state and asked to retry. | Not Run
AC-060 | FR-8.1 | Day-Of / Emergency Mode | Marking a guest Not Attending frees their seat without a full regeneration | Positive | Must | A guest is seated and linked to another guest by a rule. | 1. Mark the guest Not Attending. | Their seat becomes available immediately. No full regeneration is triggered. Any linked rule is re-evaluated. | Not Run
AC-061 | FR-8.2 | Day-Of / Emergency Mode | A walk-in guest can be added and seated without a full regeneration | Positive | Must | Day-of mode is open with at least one open seat. | 1. Add a new walk-in guest and assign them an open seat. 2. Attempt to assign a different walk-in to a seat that would break a hard rule. | Step 1 succeeds without triggering a full regeneration. Step 2 is blocked, same as any other hard-rule-breaking move. | Not Run
AC-062 | FR-8.3 | Day-Of / Emergency Mode | Two guests' seats can be swapped in one action | Positive | Must | Two seated guests with no rule conflict between their tables; a second pair whose swap would break a hard rule. | 1. Swap the first pair's seats. 2. Attempt to swap the second pair. | Step 1 completes in a single action. Step 2 is blocked with the same protection as FR-7.2. | Not Run
AC-063 | FR-8.4 | Day-Of / Emergency Mode | Day-of mode is usable and meets touch-target size on a phone | Accessibility | Should | Day-of mode is opened on a phone-sized screen. | 1. Use guest search. 2. View at-a-glance table occupancy. 3. Measure the interactive controls' touch target size. | Guest search and table occupancy are present and usable one-handed. No touch target is smaller than 44×44 CSS pixels. | Not Run
AC-064 | FR-8.5 | Day-Of / Emergency Mode | Day-of changes appear in the same history as any other edit | Positive | Should | Day-of mode is in use. | 1. Mark a guest a no-show. 2. Add a walk-in. 3. Open version/change history. | Both day-of changes appear in the same history as regular edits, with who made them and when. | Not Run
AC-065 | FR-9.1 | Export & Print | Full seating chart exports as a PDF | Positive | Must | An approved plan exists. | 1. Export the full seating chart. | A PDF is produced showing every table with its guests' names. | Not Run
AC-066 | FR-9.2 | Export & Print | Alphabetical guest-to-table lookup exports as a PDF | Positive | Must | An approved plan exists. | 1. Export the alphabetical lookup list. | A PDF lists every guest alphabetically with their assigned table. | Not Run
AC-067 | FR-9.3 | Export & Print | Place/escort cards export in a print-ready layout | Positive | Should | An approved plan exists. | 1. Export place cards. | One print-ready card per guest is produced, each showing the guest's name and table. | Not Run
AC-068 | FR-9.4 | Export & Print | Restoring a prior version is non-destructive | Positive | Must | A plan has at least 5 saved versions (v1–v5). | 1. Restore version v2. 2. Open version history. | A new version (v6) is created that copies v2's assignments. Versions v3, v4, and v5 are still present in history, not deleted. | Not Run
AC-069 | FR-10.1 | Collaboration & Notifications | An activity log shows recent changes to anyone with access | Positive | Should | Several changes have been made by different users. | 1. View the activity log. | A chronological log of recent changes is visible, correctly attributed. | Not Run
AC-070 | FR-10.2 | Collaboration & Notifications | Defined notification triggers fire correctly | Positive | Should | A plan exists and is not yet Approved. | 1. Share the plan for review; confirm the collaborator is notified. 2. Reply to a collaborator's comment; confirm they are notified. 3. Approve the plan, then change a guest's table; confirm collaborators are notified. | Each of the three defined triggers produces a notification (in-app, and by email if enabled) to the relevant collaborators. | Not Run
AC-071 | FR-10.3 | Collaboration & Notifications | Comment resolution is permission-gated and attributed | Negative | Should | A comment thread exists. One user has View-only permission; another has Edit permission but did not write the comment. | 1. Resolve the comment as the original commenter. 2. Resolve a different comment as the Edit-permission user who did not write it. 3. Attempt to resolve a comment as the View-only user. | Steps 1 and 2 succeed and show who resolved the comment and when. Step 3 is not permitted. | Not Run
AC-072 | NFR 9.1 | Non-Functional: Performance | Generation stays within target at the upper bound of scale | Performance | Should | A wedding with 500 guests and tables sufficient to seat them. | 1. Run auto-generation and time it. | Generation completes in under 60 seconds. | Not Run
AC-073 | NFR 9.1 | Non-Functional: Performance | Manual edits respond in under a second | Performance | Must | A plan is open for editing. | 1. Drag a guest to a new table and time until the UI updates, including hard-rule validation. 2. Apply a new rule and time the update. | Both actions reflect in the UI in under 1 second. | Not Run
AC-074 | NFR 9.2 | Non-Functional: Usability | A person unfamiliar with the app can use review and day-of mode unaided | Positive | Must | A person who has never used Seatwise before, and no training is given. | 1. Ask them to find a specific guest's assigned table in the review view. 2. Trigger a blocked action and ask them to explain, in their own words, why it was blocked. | They complete both tasks correctly without help from anyone familiar with the app. | Not Run
AC-075 | NFR 9.2 | Non-Functional: Usability | Every blocked action names the specific rule and guests, never a generic error | Negative | Must | A wedding has a full table, a Must-Not-Sit-Together pair, and a Restricted table. | 1. Trigger a capacity-blocked move. 2. Trigger a Must-Not-Sit-Together-blocked move. 3. Trigger a Restricted-table-blocked move. | Each of the 3 blocked actions shows a distinct, specific, plain-language message — never the same generic "action not allowed" text. | Not Run
AC-076 | NFR 9.3 | Non-Functional: Security & Multi-Tenancy | A user with no access cannot reach another wedding's data directly | Security | Must | A user has no access to Wedding X. Wedding X's internal ID or URL is known or guessable. | 1. Attempt to open Wedding X's data directly by URL/ID, bypassing the normal navigation. | Access is denied at the data layer (not merely hidden from a menu). No guest, rule, or plan data from Wedding X is returned. | Not Run
AC-077 | NFR 9.3 | Non-Functional: Security & Multi-Tenancy | Guest personal data is protected in transit and at rest | Security | Must | A wedding with guest names and accessibility/dietary notes. | 1. Inspect network traffic when loading guest data (confirm encryption in transit). 2. Confirm with the engineering team that stored data is encrypted at rest and export/retention controls are limited per policy. | Guest data is encrypted in transit and at rest; retention/export controls match documented policy. | Not Run
AC-078 | NFR 9.4 | Non-Functional: Availability | Printed materials remain usable with no connectivity | Positive | Should | A chart and alphabetical lookup list were exported and printed the day before, with no further changes since. | 1. With no internet connection, use only the printed materials to locate 5 specific guests' tables. | All 5 guests are correctly located using only the printed materials. | Not Run
AC-079 | NFR 9.5 | Non-Functional: Accessibility & Devices | The app conforms to WCAG 2.1 Level AA | Accessibility | Should | The review view and day-of mode are accessible for testing. | 1. Run an automated accessibility scan (e.g., axe) against both views. 2. Navigate both views using only a keyboard. 3. Navigate both views using a screen reader. | No critical WCAG 2.1 AA violations are reported. Every function is reachable by keyboard alone. The screen reader announces all labels and controls correctly. | Not Run
AC-080 | NFR 9.5 | Non-Functional: Accessibility & Devices | The app is usable on both desktop and mobile screen sizes | Positive | Should | A wedding with a generated plan. | 1. Use the full app on a desktop browser. 2. Use the full app on a mobile browser at common phone widths. | Layout and functionality remain usable at both sizes; day-of mode in particular is comfortable to use one-handed on a phone. | Not Run
AC-081 | §11.1–11.2 | End-to-End Scenario | Full setup-to-approval walkthrough | End-to-End | Must | A new wedding and a realistic guest spreadsheet (approx. 100 guests) are ready. | 1. Create the wedding. 2. Import the guest spreadsheet. 3. Add a few Must-Sit-Together and Must-Not-Sit-Together rules; set the Side-Mixing level. 4. Quick-create a standard set of tables. 5. Generate the plan. 6. Share it with the couple and a collaborator. 7. Have the collaborator comment, then attempt an edit that a rule blocks. 8. Have the couple mark the plan Approved. | Each step completes as described. The blocked edit in step 7 shows a clear, specific explanation. The plan ends in Approved status with every guest seated. | Not Run
AC-082 | §11.3 | End-to-End Scenario | Pre-wedding changes after approval | End-to-End | Must | An Approved plan exists from the prior scenario. | 1. Mark 2 guests Not Attending. 2. Add 1 late guest and seat them in an open seat. | Seats free up and are re-checked automatically. The new guest is seated without breaking any rule. The plan remains Approved, now showing a "Modified since approval" indicator. | Not Run
AC-083 | §11.4 | End-to-End Scenario | Day-of execution using day-of mode and printed backups | End-to-End | Must | The approved, updated plan has been exported and printed the day before. | 1. On a phone, mark a no-show guest absent in day-of mode. 2. Swap two guests' seats for a last-minute request. 3. Cross-check the printed chart and lookup list against the state before these two day-of changes. | Both day-of actions complete in under a minute each and are blocked/allowed per the normal hard/soft rule behavior. The pre-existing printed materials still correctly reflect guests' tables as of when they were printed. | Not Run
AC-084 | §7, §1 | End-to-End Scenario | Two clients' weddings never cross-contaminate across a full lifecycle | End-to-End | Must | One planner account. | 1. Fully set up Wedding A and Wedding B (distinct guests, rules, tables) under the same planner account. 2. Generate and approve both independently. 3. At every step, check that nothing from one wedding (a guest, a rule, a table, a comment) appears in the other. | Both weddings complete the entire lifecycle independently. At no point does any data cross between them. | Not Run

## Summary
Seatwise — Acceptance Test Summary
Counts update automatically from the Test Cases tab as Status values are filled in.
Feature Area | Total Tests | Pass | Fail | Blocked | Not Run / N/A | % Pass
Cross-Cutting Invariant | 3 | 0 | 0 | 0 | 3 | 0%
Account & Wedding Management | 8 | 0 | 0 | 0 | 8 | 0%
Guest List Management | 11 | 0 | 0 | 0 | 11 | 0%
Relationships & Seating Rules | 10 | 0 | 0 | 0 | 10 | 0%
Table & Venue Layout | 7 | 0 | 0 | 0 | 7 | 0%
Automated Seat Assignment Engine | 7 | 0 | 0 | 0 | 7 | 0%
Review & Approval | 6 | 0 | 0 | 0 | 6 | 0%
Manual Adjustment | 7 | 0 | 0 | 0 | 7 | 0%
Day-Of / Emergency Mode | 5 | 0 | 0 | 0 | 5 | 0%
Export & Print | 4 | 0 | 0 | 0 | 4 | 0%
Collaboration & Notifications | 3 | 0 | 0 | 0 | 3 | 0%
Non-Functional: Performance | 2 | 0 | 0 | 0 | 2 | 0%
Non-Functional: Usability | 2 | 0 | 0 | 0 | 2 | 0%
Non-Functional: Security & Multi-Tenancy | 2 | 0 | 0 | 0 | 2 | 0%
Non-Functional: Availability | 1 | 0 | 0 | 0 | 1 | 0%
Non-Functional: Accessibility & Devices | 2 | 0 | 0 | 0 | 2 | 0%
End-to-End Scenario | 4 | 0 | 0 | 0 | 4 | 0%
TOTAL | 84 | 0 | 0 | 0 | 84 | 0%
Total acceptance tests: 84, covering every functional requirement (FR-0.x–FR-10.x), every non-functional requirement, and 4 end-to-end scenarios from the PRD.